## ADO Work Items
Work Item Type | Title | Description | Acceptance Criteria | Story Points | Effort (Hours) | Priority | State | Tags | Area Path | Iteration Path
Epic | Migrate custom Python package/wheel to Fabric Spark Runtime 2.0 | Upgrade the published Python wheel from Fabric Spark Runtime 1.3 (Python 3.11, Spark 3.5) to Runtime 2.0 (Python 3.13, Spark 4.1, Delta 4.2, Azure Linux 3.0). Includes inventory, code/dependency updates, wheel rebuild, staged Environment validation, and controlled production rollout with rollback. | Wheel installs and runs cleanly in Runtime 2.0 Environment; regression suite passes; production notebooks/jobs switched with documented rollback path; Runtime 1.3 Environment retained during observation. |  |  | 1 | New | Fabric;Runtime2.0;Python;Migration | \ | \
Feature | Assessment & Inventory | Complete inventory of the package, dependencies, runtime usage, and current build process to quantify migration effort. | Dependency list with pins and native-extension notes; gap analysis of preinstalled packages; flagged PySpark/pandas API usages; documented current build process. | 5 |  | 1 | New | Assessment | \ | \
Task | Inventory package type and dependencies | Document pure Python vs native/Cython, current Python version, and all dependencies with pins. | Written inventory of package type + dependency list. |  | 2 | 2 | New |  | \ | \
Task | Compare Runtime 1.3 vs 2.0 preinstalled packages | Compare Fabric runtime inventories and identify packages that must be added explicitly in 2.0. | Gap list of packages removed from Runtime 2.0. |  | 3 | 2 | New |  | \ | \
Task | Identify PySpark / pandas API on Spark breaking changes | Scan code for iteritems, append, inplace, and other known Spark 4.x / pandas API changes. | Flagged code locations documented. |  | 3 | 2 | New |  | \ | \
Task | Document current wheel build process and CI | Capture how the current wheel is built and published. | Build process documented. |  | 2 | 2 | New |  | \ | \
Feature | Code & Dependency Compatibility | Update package metadata, dependencies, and source code for Python 3.13 and Spark 4.1 compatibility. | python_requires and dependency pins updated; no deprecation/runtime errors on 3.13; missing packages identified; unit tests green on Python 3.13. | 8-13 |  | 1 | New | Compatibility | \ | \
Task | Update python_requires and dependency pins | Raise requires-python and pin dependencies to versions that publish cp313 / manylinux wheels. | pyproject.toml/setup.py updated; dry-run install succeeds on Python 3.13. |  | 4 | 2 | New |  | \ | \
Task | Fix Python 3.13 and PySpark API incompatibilities | Apply necessary code changes for Python 3.13 and PySpark 4.x / pandas API on Spark. | No deprecation warnings or runtime errors related to known breaking changes. |  | 8-16 | 2 | New |  | \ | \
Task | Add missing packages removed from Runtime 2.0 | Prepare explicit list of packages that were preinstalled in 1.3 but removed in 2.0. | Explicit package list ready for Environment. |  | 3 | 2 | New |  | \ | \
Task | Update unit tests for Python 3.13 | Ensure test suite runs and passes under Python 3.13. | Test suite green on 3.13. |  | 4 | 2 | New |  | \ | \
Feature | Wheel Rebuild & Packaging | Rebuild the wheel targeting Python 3.13 and a Linux wheel compatible with Azure Linux 3.0 / manylinux_2_17. | Wheel filename contains cp313 (or pure py3); Linux-compatible; basic import succeeds; CI updated if applicable. | 5-8 |  | 1 | New | Packaging | \ | \
Task | Set up Python 3.13 build environment | Prepare local, WSL, or CI environment with Python 3.13 and required build tools. | python --version shows 3.13 and build tools present. |  | 3 | 2 | New |  | \ | \
Task | Rebuild wheel (cibuildwheel if native extensions) | Produce manylinux_2_17_x86_64 (or compatible) wheel for Python 3.13. | Wheel built with correct platform tag and Python version. |  | 4-8 | 2 | New |  | \ | \
Task | Validate wheel metadata and basic import | Install the wheel and verify import outside Fabric. | pip install + import succeeds. |  | 2 | 2 | New |  | \ | \
Task | Update CI pipeline for 3.13 wheel | Adjust CI to produce the Python 3.13 artifact (optional dual-build if needed). | Pipeline produces correct 3.13 wheel artifact. |  | 4 | 2 | New |  | \ | \
Feature | Fabric Environment Validation (Staged) | Validate the new wheel in an isolated Runtime 2.0 Environment before any production changes. | Environment publishes successfully; regression suite shows no functional differences vs 1.3 baseline; downstream consumers validated; rollback path documented. | 8 |  | 1 | New | Validation | \ | \
Task | Create Runtime 2.0 Environment and upload wheel | Create dedicated Environment, set Runtime 2.0, upload new wheel + missing packages, publish. | Environment publishes without dependency errors. |  | 3 | 2 | New |  | \ | \
Task | Attach Environment to representative notebooks/jobs | Attach the Runtime 2.0 Environment to copies of key notebooks and Spark job definitions. | Sessions start successfully on Runtime 2.0. |  | 2 | 2 | New |  | \ | \
Task | Execute regression suite | Run side-by-side comparison of schemas, row counts, aggregates, and critical transforms. | No material functional differences vs Runtime 1.3 baseline. |  | 8-12 | 2 | New |  | \ | \
Task | Validate downstream consumers | Confirm SQL analytics endpoint, Power BI, and pipelines can read tables written by Runtime 2.0. | Downstream consumers succeed; no unexpected protocol issues. |  | 4 | 2 | New |  | \ | \
Task | Document rollback path | Document how to reattach the Runtime 1.3 Environment if needed. | Rollback procedure written and reviewed. |  | 2 | 2 | New |  | \ | \
Feature | Production Rollout & Cleanup | Controlled production rollout of the Runtime 2.0 Environment with monitoring and eventual cleanup of 1.3 artifacts. | Pilot successful; remaining workloads migrated in batches; workspace default updated after item-level migration; 1.3 Environment archived after observation. | 5 |  | 1 | New | Rollout | \ | \
Task | Pilot on non-critical notebooks/jobs | Attach Runtime 2.0 Environment to a small set of non-critical items and monitor. | Pilot runs cleanly for observation period. |  | 3 | 2 | New |  | \ | \
Task | Expand to remaining workloads in batches | Migrate remaining notebooks and jobs in controlled batches. | All target items attached to Runtime 2.0 Environment. |  | 4 | 2 | New |  | \ | \
Task | Update workspace default runtime | Switch workspace default to Runtime 2.0 only after item-level migration is complete. | New sessions use Runtime 2.0. |  | 1 | 2 | New |  | \ | \
Task | Retire or archive Runtime 1.3 Environment | Archive or remove the old Environment after the observation period. | Cleanup complete and documentation updated. |  | 2 | 2 | New |  | \ | \

## Summary
Fabric Runtime 2.0 Upgrade Plan Summary
Epic | Migrate custom Python package/wheel to Fabric Spark Runtime 2.0
Total Story Points (Features) | 31–39
Estimated Calendar Duration | 4–6 weeks
Priority | High
Key Risk Areas | Native extensions / Python 3.13 wheels; Delta protocol changes; Spark 4.1 behavioral differences

## Import Instructions
Azure DevOps Excel Import Notes
1. This workbook is structured for Azure DevOps work item import via the Azure DevOps Excel Add-in or bulk import.
2. Required columns for most ADO imports: Work Item Type, Title. Other columns (Description, Acceptance Criteria, Story Points, Effort, Priority, Tags, Area Path, Iteration Path) are commonly supported.
3. Before import: Update Area Path and Iteration Path to match your project (currently set to '\').
4. Story Points are set on Features; Effort (Hours) are set on Tasks.
5. After import, link Tasks under their parent Features and Features under the Epic using parent-child links (or use a tree query / mapping).
6. Recommended import order: Epic → Features → Tasks, then establish parent links.
7. Adjust Priority, Assigned To, or additional fields as needed after import.
8. Official references: Microsoft Learn Runtime 2.0 migration guide.