# SOLUTION DESIGN & ESTIMATION

Great Expectations 1.24.0 Compatibility Upgrade

Restore DQ framework reliability after Spark condition processing regression

## 1. Document Control

| Field | Value |
| --- | --- |
| Title | GE 1.24.0 Compatibility Upgrade — DQ Framework |
| Status | Ready for Implementation |
| Owner | Platform Services / Data Quality |
| Related code | artifacts/data_quality.py |
| Audience | Platform Engineers, Domain Engineers |
| Date | 2026-10-29 |
| Estimation Basis | ADO-style task breakdown (hours) |

## 2. Purpose

Upgrade the Data Quality framework so it remains compatible with Great Expectations 1.24.0 and later. The change restores correct identification and quarantine of failing rows after GE altered how Spark filter conditions are returned in unexpected_index_query.

## 3. Problem Statement

Great Expectations 1.24.0 introduced a compatibility regression in Spark condition processing:

- Prior versions (≤ 1.23.1) returned unexpected_index_query as a raw SQL fragment that the framework sliced and passed to expr().

- 1.24.0+ returns a valid Python expression whose condition is a quoted SQL string (e.g. df.filter(F.expr("NOT (`col` IS NOT NULL)"))).

- The existing string-based extraction left the surrounding quotes, causing Spark to treat the predicate as a STRING and raise DATATYPE_MISMATCH.UNEXPECTED_INPUT_TYPE on the generated CASE WHEN.

- Result: DQ rules fail to flag or quarantine bad rows; pipelines either abort or silently pass invalid data.

## 4. Solution Overview

Replace the fragile string slicing with a robust parser that:

- Extracts the SQL boolean condition from both legacy and 1.24.0+ unexpected_index_query formats.

- Unwraps quoted strings and normalizes IN lists / RLIKE patterns.

- Guarantees that expr() receives a boolean expression so when() does not fail with a type mismatch.

- Adds diagnostic logging for extracted filters without changing quarantine, lookup, or event-logging behavior.

The change is isolated to data_quality.py (Expectations class). No schema, rulebook, or consumer contract changes are required.

## 5. Implementation Estimation (ADO-style)

Hours are calendar-engineering hours for a single Platform engineer familiar with the DQ framework and Spark. Includes coding, unit-level verification, and documentation. Does not include environment spin-up or full regression of every domain pipeline.

| Task | Hours | Notes |
| --- | --- | --- |
| Root-cause confirmation & GE 1.24.0 delta review | 4 | Reproduce DATATYPE_MISMATCH; confirm unexpected_index_query format change |
| Implement _extract_sql_condition + hardened _fix_gx_filter | 6 | Handle quoted/unquoted, IN, RLIKE, residual GE artifacts |
| Integrate into perform_expectations path + logging | 3 | Replace [17:-2] slice; preserve quarantine flag logic |
| Unit-level verification (sample expectations) | 4 | Null, IN-set, regex, uniqueness, lookup expectations on Spark DF |
| Regression on existing DQ rulebook (subset) | 6 | Re-run representative rules from dim_dq_rule_master |
| Documentation & release notes | 2 | Update internal README / changelog entry |
| Code review, packaging & promotion prep | 3 | PR, peer review, version bump of spark_engine wheel |
| Buffer (edge cases, environment variance) | 4 | Quoted column names, multi-condition filters, empty results |
| TOTAL | 32 | ~4 engineer-days |

Recommended calendar: 1 week (including review and limited domain validation).

## 6. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Complex multi-condition filters not fully covered by parser | Keep fallback logging; add unit tests for compound AND/OR and nested parentheses |
| Custom expectations that bypass unexpected_index_query | Confirm all production rules use standard map expectations; document any exceptions |
| GE patch releases further change the format | Parser is defensive; pin GE ≥ 1.24.0 and monitor changelog |
| Quarantine side-effects on large batches | Validate row counts and quarantine metrics on a representative dataset before promotion |

## 7. Acceptance Criteria

- DQ runs complete without DATATYPE_MISMATCH on Spark after GE 1.24.0.

- Failing rows are correctly flagged (dq_success = false) and quarantined when the rule requests it.

- Existing rulebook (null, IN-set, regex, uniqueness, lookup) continues to produce the same pass/fail outcomes on known data.

- fact_dq_error_event and fact_dq_error_event_detail receive expected rows.

- No change to published table schemas or consumer contracts.

## 8. Deliverables

- Updated spark_engine data_quality.py (or equivalent wheel).

- Unit / sample validation results.

- Short release note for Domain Engineers.

- ADO work item updated with actual hours.

End of estimation. Implementation can begin immediately using the patched data_quality.py already prepared.